### Phase 1: Discovery & Validation (Months 1–3)

Focus: Market intelligence, feasibility analysis, and strategic alignment.

Goal: A data-backed "Go/No-Go" decision.

| Timeframe | Activity / Milestone | Dependencies | Ownership |
| --- | --- | --- | --- |
| Month 1 | Market Research Deep Dive: Total Addressable Market (TAM), customer segmentation, and cultural nuances. | Internal Strategy Approval | Head of Strategy / Ext. Consultants |
| Month 2 | Competitor Analysis: Pricing, SWOT analysis, and gap identification. | Market Research Data | Product Marketing Lead |
| Month 2 | Regulatory & Compliance Audit: Identify legal barriers, tariffs, and data privacy laws (e.g., GDPR). | Target Market Selection | Legal Counsel |
| Month 3 | Financial Modeling: 3-year P&L forecast, CAPEX requirements, and ROI analysis. | Pricing Strategy | CFO / Finance Lead |
| Month 3 | MILESTONE: Go/No-Go Decision: Formal presentation to the Board/Steering Committee. | All Audit Reports | CEO / Steering Committee |

### Phase 2: Foundation & Compliance (Months 4–6)

Focus: Establishing the legal entity, protecting IP, and securing leadership.

Goal: A fully legal operating entity.

| Timeframe | Activity / Milestone | Dependencies | Ownership |
| --- | --- | --- | --- |
| Month 4 | Entity Incorporation: Filing for business registration, tax IDs, and bank accounts. | Go Decision | Legal / Finance |
| Month 4 | IP Protection: Trademarking brand names, logos, and patents in the local jurisdiction. | Entity Name Approval | Legal Counsel |
| Month 5 | Executive Hiring (Country Manager): Recruiting the local leader. | Budget Approval | HR / CEO |
| Month 6 | Location Scouting: Selecting office, retail, or warehouse space. | Entity Incorporation | Ops Manager |
| Month 6 | MILESTONE: Country Manager Onboarded: Local leadership is in place to take over daily execution. | Contract Signed | HR Lead |

### Phase 3: Localization & Infrastructure (Months 7–11)

Focus: Adapting the product/service and building the physical/digital supply chain.

Goal: A product that fits the local market (Product-Market Fit).

| Timeframe | Activity / Milestone | Dependencies | Ownership |
| --- | --- | --- | --- |
| Month 7 | Product/Service Localization: Translating UI/UX, adjusting packaging, or modifying formulas for local regulations. | Regulatory Audit (Phase 1) | Product Lead / Engineering |
| Month 8 | Supply Chain Setup: Signing 3PLs (logistics), distributors, or local suppliers. | Entity Setup | COO / Supply Chain Lead |
| Month 9 | Tech Stack Integration: Setting up local ERP, CRM, and payment gateways (local currency support). | Bank Account Setup | CTO / IT |
| Month 10 | Pricing Strategy Finalization: Finalizing local price points based on cost structure. | Supply Chain Costs | Sales Director / Finance |
| Month 11 | MILESTONE: Product Beta Ready: "MVP" version of the product/service is ready for internal testing. | Localization Complete | Product Lead |

### Phase 4: GTM Prep & Team Expansion (Months 12–15)

Focus: Building the wider team and generating pre-launch buzz.

Goal: Market awareness and sales readiness.

| Timeframe | Activity / Milestone | Dependencies | Ownership |
| --- | --- | --- | --- |
| Month 12 | Mass Hiring: Sales, Customer Support, and Marketing staff recruitment. | Office/Remote Setup | Country Manager / HR |
| Month 13 | Sales Training: Training local teams on value proposition and objection handling. | Hiring Complete | Sales Director |
| Month 14 | Soft Launch / Beta Test: Launch to a closed group (friends, family, waitlist) to test systems. | Product Beta Ready | Product / Marketing |
| Month 15 | Marketing Blitz: PR announcements, influencer campaigns, and paid ad setup. | Soft Launch Feedback | CMO / Local Marketing Lead |
| Month 15 | MILESTONE: Operational Readiness Test: Stress testing support, logistics, and IT before public open. | Staff Trained | COO / Country Manager |

### Phase 5: Launch & Stabilization (Months 16–18)

Focus: Executing the Grand Opening and optimizing based on real data.

Goal: Revenue generation and stabilization.

| Timeframe | Activity / Milestone | Dependencies | Ownership |
| --- | --- | --- | --- |
| Month 16 | MILESTONE: Grand Opening (Day 1): Official public launch. | Ops Readiness | All Hands |
| Month 16 | "Hyper-Care" Support: Daily war-room meetings to fix immediate bugs/issues. | Launch | Customer Success / Tech |
| Month 17 | First Month Review: Analyze CAC (Customer Acquisition Cost) vs. LTV (Lifetime Value). | 30 Days of Data | Finance / Strategy |
| Month 18 | Post-Mortem & Roadmap Update: Reviewing the entry project and transitioning to "Business as Usual" (BAU). | 90 Days Operations | Country Manager |

### Critical Success Factors (Governance)

To ensure this timeline holds, establish the following governance structure:

- Steering Committee: Meets monthly. (CEO, CFO, Head of Expansion).

  - Role: Approves budget variances >10% and resolves major blockers.

- Project Management Office (PMO): Meets weekly. (Project Manager + Workstream Leads).

  - Role: Tracks granular tasks and dependencies.

- Risk Register: A living document updated bi-weekly to track "Red Flags" (e.g., Visa delays for expat staff, Customs holding inventory).