## Sheet1
Launch Checklist
150+ Tasks Organized by Priority & Timeline
I. STRATEGIC FOUNDATION (Pre-Planning – 6+ Months Out)
Priority: P0 – Mission Critical
A. Concept Validation
Define core problem & target audience
Conduct competitive analysis (SWOT)
Create value proposition canvas
Run customer discovery interviews (10+ people)
Build MVP wireframes/prototype
Validate pricing model
Write 1-page vision brief
B. Business & Legal
Choose business structure (LLC, Corp, etc.)
Register business name & domain
Set up legal entity (filing)
Draft founder agreements (if team)
Open business bank account
Apply for EIN/Tax ID
Research necessary licenses/permits
Consult with business attorney
II. PRODUCT DEVELOPMENT (3–6 Months Out)
Priority: P1 – High Impact
A. MVP Build
Finalize MVP feature list (max 3 core features)
Create product roadmap (Phases 1,2,3)
Set up development environment
Build core functionality
Implement basic UI/UX
Alpha testing (internal/close circle)
Collect feedback & iterate
B. Systems & Infrastructure
Choose hosting/cloud provider
Set up version control (Git)
Configure CI/CD pipeline
Implement analytics (e.g., Mixpanel, Amplitude)
Set up error monitoring (e.g., Sentry)
Ensure GDPR/CCPA compliance basics
Set up backup & disaster recovery
C. Beta Preparation
Recruit 25–50 beta testers
Create feedback collection system
Prepare documentation/user guides
Fix critical bugs from alpha
Performance & security audit
III. PRE-LAUGH (1–3 Months Out)
Priority: P1/P2 – High/Medium Impact
A. Brand & Marketing Assets
Finalize brand name & logo
Create brand guidelines (colors, fonts, voice)
Build landing page (with waitlist/CTA)
Set up SEO basics (keywords, meta tags)
Write key website copy (Home, About, Features)
Produce 3–5 core visuals/graphics
Record demo video (90 seconds)
Design social media banners & profiles
Prepare press kit (logo, screenshots, founder bios)
Draft initial blog posts (3–5)
B. Go-to-Market Planning
Define launch goals (KPIs)
Identify launch channels (PR, social, email, etc.)
Create launch calendar/timeline
Build media outreach list (30–50 contacts)
Draft press release
Plan launch promotions/discounts
Prepare customer support FAQ
Set up social media scheduling tool
C. Sales & Operations
Set up payment system (Stripe, PayPal, etc.)
Create pricing page
Write Terms of Service & Privacy Policy
Prepare refund/return policy
Set up CRM (e.g., HubSpot, Salesforce)
Build email sequences (onboarding, nurture)
Prepare contract templates (if B2B)
D. Beta Launch
Launch beta to testers
Collect & triage feedback weekly
Run usability surveys
Fix high-priority bugs
Optimize onboarding flow
IV. LAUGH PREP (Last 4 Weeks)
Priority: P1 – High Impact
A. Final Product Polish
Complete user acceptance testing (UAT)
Mobile responsiveness check
Browser compatibility testing
Load/stress testing
Security review & penetration test
Finalize all copy (microcopy, tooltips, errors)
Implement SEO optimizations
Set up redirects (if migrating)
B. Marketing & Community
Launch email campaign sequence (pre-announce)
Schedule social media countdown (7–10 days out)
Finalize press release & embargo dates
Outreach to journalists/influencers (1–2 weeks pre)
Prepare launch day social posts
Plan Reddit/Hacker News/niche community posts
Set up referral program (if applicable)
Prepare paid ad campaigns (ready to activate)
C. Operations & Support
Finalize help center/knowledge base
Set up support ticketing system (Zendesk, Intercom)
Train support team (or prepare self-service)
Create canned responses for common questions
Set up live chat (if using)
Prepare post-launch survey
Define escalation procedures
D. Internal Readiness
Launch day team roles & schedule
Create crisis communication plan
Set up real-time dashboards (traffic, sales, errors)
Prepare post-launch retrospective meeting
V. LAUNCH WEEK (T-7 Days to L+3 Days)
Priority: P0 – Mission Critical
A. Final Checks (T-7 to T-3)
Confirm all systems operational
Test checkout/payment flow end-to-end
Test email deliverability
Backup database & code
Review all legal pages
Check all links/CTAs
Validate analytics tracking
B. Soft Launch (T-2 to T-1)
Launch to small group (friends, family)
Monitor for critical issues
Final server/performance check
C. LAUNCH DAY (T-Day)
Go live (flip switch, remove password protection, etc.)
Send launch email to waitlist
Publish press release (if using wire service)
Post on all social channels
Share with relevant online communities
Begin paid campaigns
Monitor dashboards & social mentions
Provide real-time support
Address any immediate technical issues
D. Post-Launch (L+1 to L+3)
Send follow-up “thank you” email to new users
Engage with comments/shares
Reach out to users who abandoned signup
Collect early feedback & bug reports
Send press follow-ups
Publish launch recap blog post
Thank your team & beta testers
VI. POST-LAUNCH OPTIMIZATION (L+1 Week Onward)
Priority: P2/P3 – Medium/Low Impact
A. Analyze & Iterate
Review launch KPIs vs. goals
Analyze traffic sources & conversion rates
Conduct user interview(s)
Identify top requested features
Plan first product update
A/B test landing page variations
B. Scale Marketing
Begin content marketing plan
Explore partnership opportunities
Build case studies/testimonials
Optimize SEO based on early keywords
Consider retargeting campaigns
Plan webinars/events
C. Grow Operations
Automate manual processes
Scale customer support (if needed)
Update documentation
Review security & backups
Plan next hiring phase
VII. LONG-TERM SUSTAINABILITY (Ongoing)
Priority: P3 – Foundation Building
Regular product roadmap reviews
Monthly financial review
Competitor analysis updates
Quarterly customer satisfaction surveys
Team health/performance check-ins
Industry conference planning
Network building (advisor outreach)
Explore new market opportunities
Revisit pricing strategy
Invest in team development
Update technology stack as needed
Give back (blog, open source, mentoring)
Annual strategic offsite
Celebrate milestones
BONUS: QUICKSTART PRIORITY FILTER
If you have limited time, focus only on these 30 P0 tasks:
Validate problem/solution fit
Build MVP with 1 core feature
Create landing page with waitlist
Recruit 10 beta testers
Fix critical bugs
Set up hosting & domain
Legal basics (business reg, ToS, Privacy)
Payment system
Basic analytics
Prepare support FAQ
Final UAT
Launch email sequence
Press release draft
Social profiles ready
Team roles for launch day
Post-launch feedback loop